**NORTH NEWNTON NEIGHBOURHOOD PLAN**

**2015 November Parish Plan Questionnaire**

**2016 Workshops CW, DB**

**2016 PC meetings Presentations by David King, Peter Deck and Tony McGarry on NPs**

**2017 January Parish Council meeting Vote for NP**

**2017 February Workshop CW, MM**

**2017 Feb 27th Inaugural Steering Group meeting**

 **April 3rd Second Steering Group meeting**

 **May 6th Event Village Hall – presentation**

 **June 5th Third Steering Group meeting (FR appointed Team Leader)**

 **June 20th Fourth Steering Group meeting**

 **July 4th Event Woodbridge Inn**

 **July 25th Steering Group Seven Stars – Code of Conduct and Terms of reference approved**

 **August 8th SG Meeting at the Woodbridge Inn with Jeff Bishop, Place Studio**

 **August 30th Meeting FR/VM/CW Charlton Cat – Vision and Objectives**

 **September 1st Place Studio quotation accepted**

 **September 8th Telephone conversation with Sophie Davies, WC planning FR/CW**

 **September 21 Area Designation Confirmation for NN Parish**

 **September 28 First Summary Newsletter to all the Parish – M Bohan designed**

 **September 29 Area Designation approved by WC**

 **Oct/Nov Second Summary Newsletter**

 **October Character assessments carried out throughout the parish (SG members and volunteers)**

 **Oct/Nov Work on designating “Green Spaces”**

 **November Subscribed to Parish Online**

 **November 27 Steering Group meeting**

 **December Housing Needs Survey distributed**

 **2018 January Third Newsletter Summary**

 **February 13 Drafters’ Meeting (HP/MD, PB/LB) with JB followed by**

 **SG meeting with Jeff Bishop Woodbridge**

 **Feb/March Call for Sites**

 **March Housing Needs Survey report from WC**

 **April Design Statement – working draft**

 **April 24/25 Site Assessments – JB/CW/MD and VM/PW/EB – 6 sites proposed**

 **May 3 Steering Group Meeting Village Hall**

 **May 12 APM which included display boards of NP information including progress to date and 6 sites proposed**

 **May 19 First draft of NP (FR)!**

 **Now follows (in italics) progress since June 2018 document:**

 ***June 11 Meeting with JB to discuss draft, design statement, next steps etc. MD/CW/FR***

 ***July 10 Design statement drafters’ meeting with PB/LB/MD/HP/CW to discuss latest draft and suggest changes/additions. HP to send notes to JB at Place, along with more photos of the parish***

 ***July 14 Display of NP stuff at Community BBQ***

 ***July 30 Grant approved from Locality/Groundwork for next phase of NP, in the amount of £5440, which includes Place Studio proposal of £3440 and £2000 printing, publicity, event expenses, etc.***

 ***August 3 Another site (7th) proposed – Field House, North Newnton. Site assessment carried out CW/PW***

 ***August 7 Documents sent to Spatial Planning at WC to determine whether we need an SEA. Correspondence with FR/JB and Spatial Planning – awaiting decision***

 ***Please note throughout July/August, various drafts of Design Statement, Options Appraisals, Green Spaces & 2nd and 3rd drafts of NP (JB/FR) were reviewed***

 ***September 10 Parish Council approved draft Design Statement, and Green Spaces (The Pond and Martins Close) letters to be sent to Landowners***

 ***October Discussions on way forward with Place and what still needs to be done to proceed to next stages***

 ***November 13 Steering Group meeting at The Woodbridge***

 ***November 19 PC meeting – Local Green Spaces discussed. Adoption of Housing Needs Survey Report.***

 ***November 28 FR attended NP meeting at WC Trowbridge – met with SD and others on progress with our NP and the SEA.***

 ***November 30 Fourth Summary of Activities delivered to all 210 houses in the parish***

 ***December Site on the Rushall Road – new Site Assessment for new owner/developer***

***January 2019 Parish Council meeting – Green Spaces discussed at some length. See minutes – letters approved***

***March 11 PC meeting- see minutes re delay in SEA***

***March 30 Fifth Summary of Activities delivered to all 210 houses in the parish***

***May 11 APM at Woodbridge Inn including display on NP – good attendance***

***May*  13 PC meeting – short update on NP by CW**

***July 13 Display at Community BBQ***

***July 15 Update on NP sent to PC for meeting by FR***

 **July 16 Attendance at Trowbridge WC Planning Dept by CW – still awaiting response re SEA, SD approves of Heritage and Landscape Assessments -CW relayed to JB**